## 1st Week
Date | Task | Status
29/12/2024 | Change SDR Link in Welcome page & Update label as Live | Done
29/12/2024 | Helpdesk > Dashboard - Count mismatch in Request by Category chart | Pending
30/12/2024 | New SDR changes for Relaese (Ref - User Story 267: SDR changes 30-12) | Done
31/12/2024 | New SDR Points (Ref - User Story 272: New SDR points - 31/12) | Done
31/12/2024 | Self Service > Item Request api issue on calling Bcp api (Ref - Bug 273: Item Request api issue) | Done
2025-01-01 | Support work in Self service to move some item requests from error | Done
2025-01-01 | Wrong Time issue in Cafe | Done
2025-01-01 | Website Changes (Add Form) | Done
2025-02-01 | Requested to change Website form size & Website language change load to same page | Done
2/1/2025 - 3/1/2025 | Testing Sawaid Helpdesk test environment | InProgress

## 2nd Week
Date | Task | Status
2025-05-01 | .Net double slash issue in Bcp portal Support work in mawarid | Done
2025-06-01 | Gosi link updated in Mawarid Welcome page (Ref - User Story 300) Website Profile changes Updated Sales mail content in website Support work in mawarid | Done
2025-07-01 | Tested Sawaid credentials in backend Added Insurance and Gosi as list like HR forms in Welcome page (Ref - User Story 301) Added Flight plan Api and Generated CRM link (Ref - User Story 297) Removed Incomplete work order & work order task upto Aug 15, 2024 in maintenance application (Ref - User Story 292) Added Maintenance technician filter in Helpdesk (Ref - User Story 298) | Done
08/01/2025 - 10/01/2025 | Issues fixed on Customer Support & Helpdesk in Mawarid Test Environment Tested the Customer Support & Helpdesk full flow by iterations in Mawarid Test Enviornment | Done

## 3rd Week
Date | Task | Status
2025-12-01 | Issue fixed in Item request details page (Ref - Bug 324: Self-Service - Item Request Lines are not Showing While Redirect to Details Page After Create) | Done
13/1/2025 | Flight Plan line - CRM form configuration issue | Done
14/1/2025 | Testing process on sawaid customer support by iterations Tested Mawarid Active directory | Done
15/1/2025 | Testing process on sawaid customer support by iterations Tested the fixed issues in sawaid Tested the mawarid and sawaid test active directory | Done
16/1/2025 | Testing process on sawaid customer support by iterations Tested the fixed issues in sawaid | Done
17/1/2025 | Agent portal - Import issue (Ref - Bug 342: Agent Portal - Application Import Excel Sheet Issue) Tested the fixed issues in sawaid | Done

## 4th Week
Date | Task | Status
19/1/2025 | Added Description field in Item request lines in both create and list | Done
20/1/2025 | Reviewed the Sawaid Customer Support & Helpdesk with Idhris bhai Support works in Agent portal | Done
21/1/2025 | Sawaid Active Directory redirect url issue | Done
22/1/2025 | Sawaid Customer Support and Helpdesk deployed to live Tested the Mawarid Customer Support and Helpdesk in live Support work in Mawarid | Done
23/1/2025 | Provided Helpdesk Ticket creation Api for CRM | Done
24/1/2025 | Team is working to fix the bugs in sawaid | Inprogress

## 5th Week
Date | Task | Status
26/01/2025 | 1. Added clarity and amplitude script in website and applications | Done
27/01/2025 | NO TASK
28/01/2025 | 1. ATS > Test Question Assignment issue | Done
29/01/2025 | 1. ATS > Changed the Test Name in Test Completion Certificate 2. MWD Customer Support - Invalid Recipient mail id issue while creating a ticket from system | Done
30/01/2025 | 1.Document Management System - User Create Issue 2. Support work in Document Management System | Done
31/01/2025 | NO TASK